## Exe plan
Status Indicators |  | On schedule | In progress | Completed | Behind schedule | Important Deadlines
Task | Owner | 2024-09-15 | 2024-09-21 | 2024-09-26 | 2024-09-28 | 2024-09-30 | 2024-10-01 | 2024-10-08 | 2024-10-10 | 2024-10-12 | 2024-10-14 | 2024-10-21 | 2024-11-04 | 2024-11-11 | 2024-11-21 | 2024-11-18 | 2024-11-26 | 2024-12-05 | 2025-01-13 | 2025-01-24 | 2025-02-06 | 2025-02-20 | 2025-03-06 | 2025-03-20 | 2025-03-24 | 2025-04-07 | 2025-04-21
Conops Report | All
FSR Report | All
ICD Report | All
Order required hardware | All
Become familiar with the CCS & sysconfig environments | All
Become familiar with the motor control SDK | All
Midterm Presentation | All
Subsystem Research | All
Subsystem Introduction Projects | All
Understand needed Functions/Data for the Estimator | Case
Have Code Outline Complete | Case, Tamara, Cristian
Begin porting process | Tyler
Begin writing code for Inverter/PWM for the F28P65x device | Tamara
Begin writing code for the ADC driver for F28P65x device | Cristian
Begin writing code for the Estimator for the F28P65x device | Case
Project Update Presentation | All
Begin debuging process for PWM/Inverter | Tamara
Begin debuging process for ADC driver | Cristian
Begin debuging process for Estimator | Case
Port existing solution to F28P65x | Tyler
Finish up Subsyestem Demo Requiremnts | All
Begin working on 16 ADC resolution | Cristian
Begin Working DRV8300 support | Tyler
Final Presentation | All
Subsystem Demo | All
Final Report | All
Finish Porting | All
Order Brakes | Tyler
16 Bit ADC | Cristian
12 & 16 Bit ADC Support | Tyler
64 Bit Floating point Op | Case
32 & 64 Bit Floating point Op | Tyler
Enable Oversampling | Tamara
With and Without Oversampling | Tyler
Test and Compare Preformance | All
Sysconfig support | All
Final Presentation | All
Final demo | All

## exe 404
Status Indicators |  | On schedule | In progress | Completed | Behind schedule | Important Deadlines
Task | Owner | 2025-01-13 | 2025-01-24 | 2025-02-06 | 2025-02-20 | 2025-03-06 | 2025-03-20 | 2025-03-24 | 2025-04-07 | 2025-04-21 | 2025-01-13 | 2025-01-24 | 2025-02-06 | 2025-02-20 | 2025-03-06 | 2025-03-20 | 2025-03-24 | 2025-04-07 | 2025-04-21
Finish Porting to new C2000 Device | All | bar: 2025-01-13 to 2025-01-24
Order Motor Brakes | Tyler | bar: 2025-01-13 to 2025-02-06
Create a method for Test Data Acquisition | Tyler | bar: 2025-01-13 to 2025-03-20
Add support for 16 Bit ADC | Cristian | bar: 2025-01-13 to 2025-03-20
Add support for 64 Bit Floating point Op | Case | bar: 2025-01-13 to 2025-03-20
Add Support for Oversampling | Tamara | bar: 2025-01-13 to 2025-03-20
12 & 16 Bit ADC Support | Tyler | bar: 2025-01-13 to 2025-03-20
32 & 64 Bit Floating point Op Support | Tyler | bar: 2025-01-13 to 2025-03-20
Support for solution With and Without Oversampling | Tyler | bar: 2025-01-13 to 2025-03-20
Test and Compare Preformance of all control configurations | All | bar: 2025-01-13 to 2025-04-07
Sysconfig support Strech goal | All
Final demo | All

## Val plan
Task | Specification | Result | Owner
Test Ported solution | Run the motor using the ported code on the F28P65x Device | Not working | Tyler
System Compiling | Full system compile | Untested | All
Motor control With sensor Operation | The full system of a motor using a sensor operates correctly. Porting existing sensored motor control software onto 02x launch pad successfully. | Passed | Tyler
SysConfig support | The system correctly operates using the SysConfig IDE | Untested | All
16 Bit ADC resolution | The system correctly operates using 16-bit ADC resolution | Untested | Cristian
12 Bit & 16 Bit ADC resolution Support | The system correctly operates using either 12-bit or 16-bit ADC resolutions | Untested | Cristian
64-bit Floating point operation | The system Correctly Operates using 64-bit Floating Point | Untested | Tyler
32-bit & 64-bit Floating point operation | The system Correctly Operates using either 32-bit or 64-bit Floating Point | Untested | Tyler
Test 12 vs 16 Bit performance | Test the accuracy of both 12-bit and 16-bit ADC resolutions when compared to a motor with a sensor | Untested | All
Test 32-bit & 64-bit Floating point operation | Test the accuracy of both 32-bit and 64-bit ADC Floating point operations when compared to a motor with a sensor | Untested | All
Test the effectiveness of oversampling | Test the effectiveness of oversampling by comparison to the old system using a sensor(older board did not support oversampling) | Untested | All